## Slide 1: Working with a contractor to deliver a Shiny dashboard
Iris Oren
Iris.Oren@gov.scot
Energy and Climate Change Analysis
Office of the Chief Economic Advisor

## Slide 2: The business need
Climate Change Plan
Scottish TIMES Model
Finds least cost solution for Scotland to meet climate change targets
Thousands of input and output variables
Challenge to QA data and results
Diverse stakeholders from sectors across gov – differing questions
Querying model for bespoke results – time consuming for modelling team
Plan for Scotland to meet GHG targets (net zero by 2045)

## Slide 3: The business need
Scottish TIMES Model
Results
Interactive
R-Shiny dashboard
Stakeholders
Feedback for next round of modelling
Benefits
Increase stakeholder engagement
Increase trust in model
Increase model robustness
Allow users to explore full richness of model solution
Free time for TIMES team to focus on modelling
Challenge
Small TIMES team
1 member with R-coding experience
Solution: Procured dashboard

## Slide 4: Procurement
Business case for dashboard
Invitation to tender:
What do we need?
Stakeholder engagement to learn user needs
Develop PoC
Feedback from PoC to final product
Ensure that SG can host internally
Include accessibility
How will we work together?
How will work be divided between SG Analysts and Contractor?
Plan for ensuring product can be maintained
Include handover requirements in ITT
Who to invite to tender?
DataLab identified potential bidders
Three shortlisted

## Slide 5: Development
Five month project
Forecast Team:
  1 Project manager,
  1 Developer (IT) – Shiny
  2 Data engineers/support. Hosting, stakeholder engagement, documentation
SG:
  1 Analyst (IO) – Data preprocessing
Non-disclosure agreement setup

## Slide 6: Development
Stakeholder workshops
Product specification document
Forecast + SG
prioritise
requirements
IT + IO
PoC
Data eng + AWB
Hosting solution
Full product
IT + IO
Live dashboard
May 2022
June 2022
July 2022
Sep 2022

## Slide 7: Project management
Agile project management
Tools:
  SG Teams: Forecast added as guests. Day-to-day communication
  Version control: Git
  GitHub Issue tracking: Log project issues and discussions
  Project management: GitHub Project - direct link to code repository

## Slide 8: Project management
GitHub Issue tracking

## Slide 9: Project management
Agile project management
Tools:
  SG Teams: Forecast added as guests. Day-to-day communication
  Version control: Git
  GitHub Issue tracking: Log project issues and discussions
  Project management: GitHub Project - direct link to code repository

## Slide 10: Project management
GitHub Project feature

## Slide 11: Project management
GitHub Project feature

## Slide 12: Hosting
SG Analytical Workbench Shiny server
Forecast access AWB through own VPN
Support from AWB team to deploy
Dashboard accessed through secure login – individual usernames and passwords

## Slide 13: The product

## Slide 14: The product
Detailed view flows

## Slide 18: Handover
Commented code
Full documentation of current dashboard
Dependencies mapped out
Instructions for updating, adding features
Details of optional features left in repository
Sign-off by SG
Editable documentation to allow SG to continue development

## Slide 19: Benefits
Deliver a complete product under time constraints
Amplify SG resource
Learning for SG analyst - working as part of a software development team

## Slide 20: Lessons learned
Prioritise essential features (there will always be nice-to-haves)
Stakeholder workshops useful – but limit size and number
Organise code/project from the start to allow hosting
Accept that you will run into issues.
Agile principles allow responsiveness
Communication made project success (build this into ITT)